## Introduction
AI Implementation Checklist for CDFIs
This phased checklist provides a roadmap for CDFIs implementing AI solutions.
The checklist is organized into five distinct phases to help you track progress.
Each phase includes specific tasks and considerations for successful AI adoption.
PHASE 1: Data Foundation & Quick Wins (0-6 months)
PHASE 2: Data Infrastructure Enhancement (3-12 months)
PHASE 3: Advanced AI Applications (9-18 months)
PHASE 4: AI Governance & Ethical Framework (12-24 months)
PHASE 5: Scaling & Innovation (18+ months)
Use this checklist to assess your current state and plan your AI journey.
For each item, mark: "Not Started", "In Progress", "Completed", or "N/A"
Created by Clarity Impact Finance

## Phase 1
Category | Task | Success Criteria | Status | Notes
Organizational Assessment | Define clear business objectives for AI implementation | Documented AI strategy aligned with business goals
Organizational Assessment | Identify pain points and inefficiencies in current processes | Prioritized list of processes for improvement
Organizational Assessment | Assess organizational readiness for AI adoption | Readiness assessment report with recommendations
Data Assessment | Conduct data audit to inventory existing data sources | Complete inventory of all data assets
Data Assessment | Evaluate data quality and completeness | Data quality score for critical datasets
Data Assessment | Identify data gaps and create plan to address them | Data collection plan for missing information
Data Assessment | Begin basic data standardization for key datasets | Standardized data formats for key fields
Quick Wins | Implement document analysis tool for loan applications | Reduction in document processing time by 30%
Quick Wins | Deploy chatbot for basic customer inquiries | Reduced response time for common questions
Quick Wins | Use Excel-based data analysis with AI plugins | Enhanced reporting capabilities
Quick Wins | Implement basic automation for repetitive tasks | Time savings from automated processes
Quick Wins | Integrate with third-party APIs for automated data collection | Increased data collection efficiency
Training & Education | Provide AI literacy training to leadership team | Executive team understands AI potential and limitations
Training & Education | Educate staff on basic AI concepts and applications | 80% of staff complete basic AI training
Training & Education | Develop glossary of AI/ML terms for staff reference | Common AI terminology understood across organization

## Phase 2
Category | Task | Success Criteria | Status | Notes
Data Infrastructure | Implement centralized data warehouse | Single source of truth for organizational data
Data Infrastructure | Develop data pipeline for automated collection | Automated data flows from key systems
Data Infrastructure | Implement data cleaning and normalization processes | Consistent data quality across systems
Data Infrastructure | Create data dictionary and documentation standards | Comprehensive data documentation available
Data Governance | Establish data governance committee | Active governance committee meeting regularly
Data Governance | Define data ownership and access protocols | Clear protocols documented and followed
Data Governance | Create data quality monitoring processes | Regular data quality reports generated
Advanced Data Collection | Deploy enhanced data capture forms and interfaces | Digital-first data collection reducing manual entry
Advanced Data Collection | Implement digital document management system | All documents digitized and searchable
Advanced Data Collection | Integrate internal and external data sources | Comprehensive dataset incorporating external data
AI Tool Expansion | Deploy predictive analytics for loan performance | Early warning indicators for portfolio risk
AI Tool Expansion | Implement ML-based risk assessment tools | More nuanced risk assessment capabilities
AI Tool Expansion | Deploy AI-powered financial analysis tools | Faster, more accurate financial analysis
Training & Change Management | Provide specialized AI training for data analysts | Data team capable of building basic ML models
Training & Change Management | Develop change management plan for AI adoption | Staff actively engaged with AI implementation

## Phase 3
Category | Task | Success Criteria | Status | Notes
Advanced Analytics | Implement machine learning for credit scoring | More accurate risk assessment and reduced defaults
Advanced Analytics | Deploy AI for market analysis and opportunity identification | New market opportunities identified through AI
Advanced Analytics | Develop impact prediction models | Impact metrics predicted with greater accuracy
Advanced Analytics | Implement portfolio optimization algorithms | Optimized portfolio allocation based on multiple factors
Process Automation | Automate underwriting process with AI | 50% reduction in underwriting processing time
Process Automation | Deploy intelligent document processing across operations | 80% of document processing fully automated
Process Automation | Implement AI-driven compliance monitoring | Real-time compliance monitoring and alerts
Customer-Facing AI | Launch AI-powered customer service platform | 24/7 AI-powered customer support available
Customer-Facing AI | Implement personalized digital experience for borrowers | Personalized borrower portal with AI assistance
Customer-Facing AI | Deploy borrower early-warning system | Early intervention reducing default rates
Integration & Scaling | Integrate AI systems with core banking platform | Seamless data flow between AI and core systems
Integration & Scaling | Implement API-first architecture for AI services | AI capabilities available through standardized APIs
Integration & Scaling | Develop AI microservices for reusable components | Modular AI components that can be reused
Specialized Training | Provide advanced AI training for technical staff | Technical team capable of customizing AI solutions
Specialized Training | Train business staff on AI-enhanced decision making | Staff confidently using AI insights in decision making

## Phase 4
Category | Task | Success Criteria | Status | Notes
Ethical AI Framework | Develop AI ethics principles for your CDFI | Documented AI ethics principles aligned with mission
Ethical AI Framework | Establish ethical review process for AI applications | All AI applications reviewed for ethical considerations
Ethical AI Framework | Create AI impact assessment methodology | Impact assessments conducted for all AI deployments
Ethical AI Framework | Develop community engagement plan for AI initiatives | Community feedback incorporated into AI development
Governance Structure | Form AI governance committee with diverse representation | Active governance committee with quarterly meetings
Governance Structure | Establish AI development and deployment protocols | Clear protocols for AI development lifecycle
Governance Structure | Create model governance framework | Model inventory with documented governance
Compliance & Risk | Implement AI risk management framework | Comprehensive AI risk register maintained
Compliance & Risk | Develop AI compliance documentation standards | Complete compliance documentation for all AI systems
Compliance & Risk | Create audit procedures for AI systems | Regular audits of AI systems conducted
Fairness & Bias | Implement bias detection and mitigation processes | Reduction in biased outcomes from AI systems
Fairness & Bias | Establish equity metrics for AI applications | Equity metrics tracked and improving over time
Fairness & Bias | Develop remediation procedures for biased outcomes | Prompt remediation of any identified bias issues
Transparency | Create explainability guidelines for AI models | All AI models meeting explainability standards
Transparency | Establish transparency protocols for AI-based decisions | Transparent disclosures about AI use to stakeholders

## Phase 5
Category | Task | Success Criteria | Status | Notes
Scaling AI Capabilities | Scale successful AI applications across organization | AI capabilities available across all departments
Scaling AI Capabilities | Implement enterprise AI platform | Centralized platform for managing AI applications
Scaling AI Capabilities | Establish AI Center of Excellence | Active Center of Excellence driving adoption
Innovation | Pilot emerging AI technologies | Regular pilots of new AI technologies
Innovation | Implement AI innovation sandbox environment | Innovation sandbox used for testing new ideas
Innovation | Develop AI research partnerships with academic institutions | Active research partnerships with universities
Partnerships | Establish AI vendor management framework | Effective management of AI vendor relationships
Partnerships | Create CDFI AI consortium for shared resources | Active participation in CDFI AI consortium
Partnerships | Develop open source AI tools for CDFI sector | Contribution to open source AI tools for CDFIs
Advanced Impact | Implement advanced impact measurement with AI | Sophisticated impact metrics powered by AI
Advanced Impact | Develop predictive community impact models | Accurate predictions of community outcomes
Advanced Impact | Create AI-powered community needs assessment | Data-driven community needs assessment process
Continuous Improvement | Implement continuous learning for AI models | AI models that improve automatically over time
Continuous Improvement | Establish formal AI maturity assessment process | Regular assessment of AI maturity with improvements
Continuous Improvement | Create long-term AI innovation roadmap | Strategic roadmap guiding long-term AI innovation

## Success Stories
CDFI Success Stories: AI Implementation
Piedmont Community Lenders (PCL)
PCL started with a simple document analysis tool to process loan applications faster. This quick win reduced processing time by 40% while improving accuracy. Building on this success, they implemented data standardization and centralized storage before moving to more advanced AI applications over an 18-month period.
Key Lessons:
• Start with a clear business problem and measurable outcomes
• Focus on data quality before implementing sophisticated AI
• Ensure staff are trained and comfortable with new tools
• Regularly measure and communicate impact of AI initiatives
Horizon Community Capital
Horizon created an "AI roadmap" that began with basic process automation and gradually expanded to credit scoring and risk assessment. Their phased approach allowed them to build staff capabilities while demonstrating value. After 24 months, they had fully integrated AI into core operations, with significant improvements in efficiency and loan performance.
Key Lessons:
• Develop a phased implementation plan with clear milestones
• Address data gaps early in the process
• Create a governance structure to oversee AI initiatives
• Balance innovation with mission alignment and ethical considerations